## Slide 1
RWDPLATFORM / GOVERNED ANALYTICS DELIVERY
Product | Implement the full RWD analytics workflow
First release · Months 1–5
Vision: a governed, reusable workflow for RWD data products and study analytics across GSK therapeutic areas.
FIRST RELEASE
Two initial use cases (confirmed in Month 1), from approved specification and qualified source data to reproducible datasets, analyses, reconciled TFLs and dashboards.
STARTING POINT
Existing specification-builder and R-module components are assessed, reused and integrated; release readiness is shown through the gates.
DEPENDS ON
Upstream OMOP conversion · Clinical definitions layer · Supported R runtime on Databricks (confirmation due M1) · AI governance approval · Hosting · TA experts
DELIVERABLE
AI ASSISTANCE
PLAN
FOUNDATIONS
BUILD + INTEGRATE
Month 1
Month 2
Month 3
Month 4
Month 5
A SCIENTIFIC INTENT, DEFINITIONS & DATA READINESS
F01
Researcher Portal & Specification Builder
Request, reuse and revise studies; review specifications with sheet-and-row traceability
Maps protocol concepts to candidate OMOP vocabulary terms for review
Delivered elsewhere · integrated here
F02
Functional Contract Library
Machine-readable, approved instructions for each dataset and analysis, including variable mapping and temporal rules
Drafts definitions and flags what the specification leaves open
F03
Clinical Definitions Integration
Approved concept sets with identifier, version, intended use and exclusions, referenced by contracts
Retrieves candidate concepts and flags ambiguity for review
Delivered elsewhere · integrated here
F04
Source Qualification & Study-Variable Mapping
Assesses source suitability and supplies the source fields that contract mappings reference; clinical notes optional
Proposes variable-to-source bindings for review
Delivered elsewhere · integrated here
B ANALYTICAL EXECUTION & EVIDENCE OUTPUTS
F05
Analysis Dataset Engine
Implements approved clinical rules on qualified sources and assembles verified, reusable longitudinal products and study datasets
Drafts code for missing rules and explains sequence decisions for review
F06
Reusable Study Analysis Packages
Analyses and standard plots on the standard ADS: attrition, baseline tables, treatment patterns, outcomes, resource use and incidence
Drafts analysis configuration; reviewed modules estimate
F07
Evidence Outputs: TFLs & Insight Views
Versioned results rendered into TFL packages, plus feasibility and data-quality views with denominators visible
Drafts narratives and summaries; flags anomalies for review
ACCEPTANCE GATES | LT DECISION: ENDORSE INITIAL SCOPE, CONFIRM DELIVERY AND REVIEW CAPACITY, SECURE SOURCE, RUNTIME AND DEFINITION DEPENDENCIES
M1 · SCOPE & READINESS AGREED
Use cases, sources and runtime agreed
M3 · FIRST SPEC-TO-DATASET WORKFLOW
Demonstrated on test inputs
M4 · CONTRACTS EXECUTION-READY
Definitions and source bindings approved
M5 · FIRST RELEASE DECISION
Use cases accepted for controlled use
Notes: Opening: we already have components we can build on. This proposal connects them into one governed workflow, from an approved specification and qualified source data through to a reproducible dataset, selected analyses, TFLs and dashboards. The architecture is designed to extend across GSK therapeutic areas, but the five-month commitment is the first integrated release, demonstrated on two initial use cases confirmed in month 1. We reuse existing components, encode approved study requirements in contracts, and combine reviewed derivation libraries with controlled AI-generated extensions where needed. Success is not that AI writes every line; it is that users obtain scientifically checked, reproducible datasets and outputs, reuse accepted work, and operate the service with explicit release controls. Success is measured by scientific correctness, reuse, user effort and release evidence, not by whether every component has been coded.
What exists today: the specification builder and a library of R analysis modules. In month 1 each is assessed for its available version, what it has demonstrated, and the qualification and integration work remaining, so that "exists" is not read as "qualified".
The researcher portal and specification builder (F01), clinical definitions integration (F03) and source qualification and mapping (F04) are already built or being delivered elsewhere; this plan integrates them rather than rebuilding them. Variable mapping is specified in the functional contract (F02): each variable is classed as direct, derived, a mixture or a constant, with its source fields, rule or fixed value, so source work supplies where data lives and the contract defines what each variable means. The supporting slides give detailed plans for F02, F05, F06 and F07.
How to read the plan: workstreams run in parallel, using clearly labelled test inputs until approved inputs are available. Acceptance gates control when approved inputs are used and when a release is promoted. Month 1: use cases, source coverage, runtime and methods agreed. Month 3: a first specification-to-dataset workflow is demonstrated on test inputs, so integration problems surface early rather than in the final month. Month 4: clinical definitions and source bindings are approved, so contracts become execution-ready. Readiness follows one progression throughout: implemented on test inputs, integrated candidate, independently qualified, accepted for controlled use. Month 5: a first-release decision for the two use cases, based on independent dataset and numerical checks and user acceptance.
AI assistance: AI interprets, proposes and investigates. Deterministic software executes and checks. Authorized people approve scientific intent, material configuration changes and release decisions; routine execution follows those approved instructions.
Complex treatment-sequence designs, such as lines of therapy in oncology or biologic switching in respiratory and immunology: supported rules are configured through reviewed parameters in the contract and executed by the engine. Rules outside the validated capability set need a reviewed extension and additional testing, with explicit test cases for overlaps, gaps, switches, combination changes and restarts.
Dependencies and when they are needed: a supported R runtime on Databricks confirmed in month 1; upstream OMOP conversion for the pilot sources by month 3; clinical definitions for the pilot use cases by month 4; AI governance approval before AI assistance is used on data; hosting before any user-facing view. If an approved input is late, the month 5 decision is conditional on it.
Decision requested from LT: confirm the two initial use cases and release scope, protected delivery and review capacity, and who will provide the source, runtime and clinical-definition dependencies.
Resourcing: indicatively three to four engineers plus protected scientific, method and QC time, confirmed at the investment gate.

## Slide 2
RWDPLATFORM / GOVERNED ANALYTICS DELIVERY
F02 | Functional Contract Library
F02 · Months 2–3
Functional contract: the machine-readable, approved instructions defining what each dataset and analysis must do.
OUTCOME
Contracts become definition-complete in Month 3 and execution-ready in Month 4, once required concept sets, source bindings and engine support are accepted.
DEPENDS ON
Specification builder output (F01) · Contract format decision (Month 1) · Source fields from source qualification (F04) · Concept sets (F03)
DELIVERABLE
AI ASSISTANCE
DESIGN + MAPPING
TRACEABILITY, READINESS + RELEASE
Month 2
Month 3
A CONTRACT DESIGN & VARIABLE MAPPING
F02.1
Contract Standard & Schema
Defines the required structure of every contract: population, index date, variables and their mapping type, endpoints and time windows
F02.2
Standard Variable Library
Master variable definitions with parameters, TA examples and citations; reviewers confirm each definition and default used
Recommends reusable variables per study
F02.3
Variable Mapping Specification
Each variable gets a mapping type (direct, derived, mixture, constant) and a readiness status (supported, pending, unavailable)
Proposes mapping type and candidate source fields for review
F02.4
Automated Specification Conversion
Supported specification fields convert automatically; ambiguities and unsupported rules are routed for review
Proposes structured parameters from free-text rules
B TRACEABILITY, READINESS & CHANGE CONTROL
F02.5
Specification Traceability
Links every contract element back to its specification line and protocol section for audit
Maps contract elements to protocol sections
F02.6
Contract Readiness Review
Four checks: structurally valid, scientifically reviewed, supported by available data, supported by the engine
Flags gaps and inconsistencies for reviewers
F02.7
Change Control & Decision Log
Records every contract version, who drafted and accepted each definition, and clinical rulings with rationale
Summarizes changes for reviewers
F02.8
Pilot Contract Definitions
Definition-complete contracts for the initial use cases; every variable has a documented mapping disposition
ACCEPTANCE GATES | WORKSTREAMS RUN IN PARALLEL; GATES CONTROL USE OF APPROVED INPUTS AND PROMOTION OF RELEASES
MID MONTH 2 · STANDARD APPROVED
Contract structure and mapping types signed off
EARLY MONTH 3 · CONVERSION OPERATIONAL
Supported fields convert; ambiguities routed for review
END OF MONTH 3 · PILOT DEFINITIONS COMPLETE
Source and capability dependencies identified
Notes: F02 Functional Contract Library runs across months 2 to 3. Contracts become definition-complete in Month 3 and execution-ready in Month 4, once required concept sets, source bindings and engine support are accepted.
F02.1 Contract Standard & Schema, early to mid month 2: Defines the required structure of every contract: population, index date, variables and their mapping type, endpoints and time windows.
F02.2 Standard Variable Library, mid month 2 to early month 3: Master variable definitions with parameters, TA examples and citations; reviewers confirm each definition and default used.
F02.3 Variable Mapping Specification, mid month 2 to mid month 3: Each variable gets a mapping type (direct, derived, mixture, constant) and a readiness status (supported, pending, unavailable).
F02.4 Automated Specification Conversion, mid month 2 to early month 3: Supported specification fields convert automatically; ambiguities and unsupported rules are routed for review.
F02.5 Specification Traceability, late month 2 to mid month 3: Links every contract element back to its specification line and protocol section for audit.
F02.6 Contract Readiness Review, early to mid month 3: Four checks: structurally valid, scientifically reviewed, supported by available data, supported by the engine.
F02.7 Change Control & Decision Log, early to mid month 3: Records every contract version, who drafted and accepted each definition, and clinical rulings with rationale.
F02.8 Pilot Contract Definitions, mid to late month 3: Definition-complete contracts for the initial use cases; every variable has a documented mapping disposition.
Each variable records two separate attributes: its mapping type (how it is produced) and its readiness (supported, pending evidence or implementation, or unavailable). Required variables must be supported before execution; unavailable variables are never silently filled. The contract holds the variable mapping specification. Direct variables reference a source field; derived variables reference a contract rule that the engine (F05) executes; a mixture combines candidate source fields under an explicit selection or precedence rule; and constants are set in the contract. Source qualification (F04) supplies the available fields, so source work defines where data lives and the contract defines what each variable means. The contract refers to concept sets (F03) but does not contain them, and it holds no executable code. Defaults from the variable library are never inherited silently: the reviewer confirms the definition, its applicability and its parameter values.
AI assistance here: recommends reusable variables per study; proposes mapping type and candidate source fields for review; proposes structured parameters from free-text rules; maps contract elements to protocol sections; flags gaps and inconsistencies for reviewers; summarizes changes for reviewers. AI interprets, proposes and investigates; deterministic software executes and checks; authorized people approve scientific intent, material configuration changes and releases.
Acceptance gates: Standard approved (mid month 2); Conversion operational (early month 3); Pilot definitions complete (end of month 3).
Depends on: Specification builder output (F01); Contract format decision (Month 1); Source fields from source qualification (F04); Concept sets (F03).

## Slide 3
RWDPLATFORM / GOVERNED ANALYTICS DELIVERY
F05 | Analysis Dataset Engine
F05 · Months 3–5
Config-driven: approved clinical rules are implemented on qualified sources, assembled into reusable products and study datasets, and verified patient by patient.
OUTCOME
For the agreed use cases: versioned datasets with explicit source support, tested derivation logic, reproducible execution and independent acceptance evidence.
DEPENDS ON
Execution-ready contracts (F02) · Source fields and readiness (F04) · Package input needs (F06) · Databricks environment · Independent reviewers
DELIVERABLE
AI ASSISTANCE
DESIGN + FIRST BUILD
CLINICAL LOGIC + REUSE
QC + RELEASE
Month 3
Month 4
Month 5
A DESIGN & REUSE
F05.1
Standard Dataset Design
Row meaning, keys and relationships for longitudinal, episode and study-level outputs, and the inputs each F06 package needs
F05.2
Reuse & Gap Assessment
Pilot rule-coverage matrix (reuse, configure, adapt, new, excluded); source bindings and R module interfaces qualified
F05.3
Automated Build Planning
Resolves contract rules into versioned implementations and run order; blocks builds with missing parameters or unsupported inputs
B CLINICAL LOGIC
F05.4
Cohort & Endpoint Derivation
Eligibility, index, window, record-selection and censoring rules, checked against independently specified cases
F05.5
Treatment Pathway Derivation
The agreed overlap, gap, combination, switch and restart rules, with patient timelines verified
Explains sequence assignments for reviewers
F05.6
New Rule Development
Missing rules built against approved requirements and made selectable in the contract; library reuse decided separately
Drafts candidate code for missing rules
C BUILD, QC & RELEASE
F05.7
Dataset Build & Assembly
Runs the accepted build plan, assembles study datasets and stops partial or stale results being treated as complete
F05.8
Independent QC & Traceability
Material derivations traced to source records; reference cases and whole-delivery integrity reconciled
Investigates discrepancies for reviewers
F05.9
Dataset Release & Reuse
The exact build accepted; two studies shown reusing one longitudinal product, with study-specific steps verified
ACCEPTANCE GATES | WORKSTREAMS RUN IN PARALLEL; GATES CONTROL USE OF APPROVED INPUTS AND PROMOTION OF RELEASES
LATE MONTH 3 · FIRST BOUNDED BUILD
Test contract runs through the intended build path
LATE MONTH 4 · REUSE DEMONSTRATED
Two study definitions share one versioned longitudinal product
END OF MONTH 5 · PILOT DATASETS ACCEPTED
Reference, integrity, reproducibility and release criteria met
Notes: F05 Analysis Dataset Engine runs across months 3 to 5. For the agreed use cases: versioned datasets with explicit source support, tested derivation logic, reproducible execution and independent acceptance evidence.
F05.1 Standard Dataset Design, early to mid month 3: Row meaning, keys and relationships for longitudinal, episode and study-level outputs, and the inputs each F06 package needs.
F05.2 Reuse & Gap Assessment, early to mid month 3: Pilot rule-coverage matrix (reuse, configure, adapt, new, excluded); source bindings and R module interfaces qualified.
F05.3 Automated Build Planning, mid to late month 3: Resolves contract rules into versioned implementations and run order; blocks builds with missing parameters or unsupported inputs.
F05.4 Cohort & Endpoint Derivation, mid month 3 to mid month 4: Eligibility, index, window, record-selection and censoring rules, checked against independently specified cases.
F05.5 Treatment Pathway Derivation, late month 3 to late month 4: The agreed overlap, gap, combination, switch and restart rules, with patient timelines verified.
F05.6 New Rule Development, late month 3 to early month 5: Missing rules built against approved requirements and made selectable in the contract; library reuse decided separately.
F05.7 Dataset Build & Assembly, early month 4 to mid month 5: Runs the accepted build plan, assembles study datasets and stops partial or stale results being treated as complete.
F05.8 Independent QC & Traceability, early month 3 to mid month 5: Material derivations traced to source records; reference cases and whole-delivery integrity reconciled.
F05.9 Dataset Release & Reuse, late month 4 to late month 5: The exact build accepted; two studies shown reusing one longitudinal product, with study-specific steps verified.
Configuration is how users control the build; it is not where the implementation complexity disappears. This workstream establishes the supported data structures, implements and qualifies the clinical derivations, connects existing modules to the selected sources, and verifies the complete patient-level outputs. Existing components are mapped to these work packages and reused where the evidence supports it. Design first: every output has an explicit row meaning, keys and relationships, because attrition, treatment patterns, time-to-event analysis and incidence each need different inputs; the pilot rule-coverage matrix records, for each required rule, the existing implementation, supported parameters, source prerequisites, tests and remaining work, and that matrix is what justifies the timeline. Two kinds of adapter: a source adapter translates a delivered source into the engine’s inputs, and a module interface connects an existing R module to them. Modules that derive study variables run here; modules that estimate quantities belong to the analysis packages (F06). Existing modules are reused through qualified interfaces where the source supports their required structure and meaning; unsupported source and module combinations stay blocked or need a reviewed extension. A native-source route is used only if an initial use case needs it, with source mapping handed over explicitly from F04. A rule may fail to execute for three reasons: an incomplete scientific instruction goes back to definition review, a missing source fact is resolved or taken out of scope, and only a clear rule without an implementation is built as a controlled extension, with its schema and tests updated so the contract can select it. Reuse means three different things: reusable code, reusable longitudinal data and reusable derived variables. Underlying events can be shared while study-specific selections, such as a baseline value over a different window, are derived again, and a treatment sequence is reused only when its construction rules and source version match. Acceptance has four levels: rule correctness against independent cases, whole-delivery integrity, execution and reproducibility at the intended scale, and release and change control tied to the exact dataset, code, configuration and source version. We reuse code and longitudinal data where the definitions genuinely match; where a requirement is unsupported, the system exposes the gap and follows a reviewed implementation path rather than silently producing a plausible dataset.
AI assistance here: explains sequence assignments for reviewers; drafts candidate code for missing rules; investigates discrepancies for reviewers. AI interprets, proposes and investigates; deterministic software executes and checks; authorized people approve scientific intent, material configuration changes and releases.
Acceptance gates: First bounded build (late month 3); Reuse demonstrated (late month 4); Pilot datasets accepted (end of month 5).
Depends on: Execution-ready contracts (F02); Source fields and readiness (F04); Package input needs (F06); Databricks environment; Independent reviewers.

## Slide 4
RWDPLATFORM / GOVERNED ANALYTICS DELIVERY
F06 | Reusable Study Analysis Packages
F06 · Months 4–5
Ready-to-run analysis packages built on the existing R module library, reading the dataset structures defined in F05.
OUTCOME
Supported analyses run on datasets that meet each package’s required structure, variable definitions and assumptions, with diagnostics and reference results.
DEPENDS ON
Analysis datasets (F05) · Existing R module library · Supported R runtime on Databricks (confirmation due Month 1)
DELIVERABLE
AI ASSISTANCE
CORE STUDY ANALYSES
OUTCOMES, RESOURCE USE + QUALIFICATION
Month 4
Month 5
STUDY ANALYSIS PACKAGES
F06.1
Cohort Attrition & Baseline Characteristics
Automated attrition flow and baseline characteristics table by cohort, with standardized differences
Drafts the analysis configuration for review
F06.2
Standard Plot Library
Ready-made plots: attrition diagrams, Kaplan–Meier curves, treatment flow (Sankey) charts, forest plots and distributions
Suggests the plot type for each result
F06.3
Treatment Patterns & Drug Utilization
Treatment sequences, switching, persistence, time to discontinuation and adherence as proportion of days covered
Drafts pathway configuration for review
F06.4
Clinical Outcomes & Time-to-Event
Kaplan–Meier with medians and confidence intervals, Cox models, time to next treatment and event rates, with diagnostics
Drafts model configuration; reviewed modules estimate
F06.5
Healthcare Resource Use & Costs
Visits, hospitalizations and procedures per patient-year; costs only where the source cost basis supports them
F06.6
Incidence & Prevalence
Incidence rates and point/period prevalence, with explicit denominator populations, observation rules and CIs
F06.7
Study Templates & Qualification Records
Pre-configured packages with inputs, assumptions and diagnostics, each qualified against independent reference results
Recommends a template from the protocol
ACCEPTANCE GATES | WORKSTREAMS RUN IN PARALLEL; GATES CONTROL USE OF APPROVED INPUTS AND PROMOTION OF RELEASES
END OF MONTH 4 · CORE ANALYSES AVAILABLE
Attrition, baseline and treatment patterns from the ADS
MID MONTH 5 · OUTCOMES READY FOR QUALIFICATION
Outcomes, resource use and incidence integrated
END OF MONTH 5 · PACKAGES QUALIFIED
Reference tests passed; qualification records complete
Notes: F06 Reusable Study Analysis Packages runs across months 4 to 5. Supported analyses run on datasets that meet each package’s required structure, variable definitions and assumptions, with diagnostics and reference results.
F06.1 Cohort Attrition & Baseline Characteristics, early to mid month 4: Automated attrition flow and baseline characteristics table by cohort, with standardized differences.
F06.2 Standard Plot Library, early to mid month 4: Ready-made plots: attrition diagrams, Kaplan–Meier curves, treatment flow (Sankey) charts, forest plots and distributions.
F06.3 Treatment Patterns & Drug Utilization, month 4: Treatment sequences, switching, persistence, time to discontinuation and adherence as proportion of days covered.
F06.4 Clinical Outcomes & Time-to-Event, mid month 4 to early month 5: Kaplan–Meier with medians and confidence intervals, Cox models, time to next treatment and event rates, with diagnostics.
F06.5 Healthcare Resource Use & Costs, mid month 4 to mid month 5: Visits, hospitalizations and procedures per patient-year; costs only where the source cost basis supports them.
F06.6 Incidence & Prevalence, mid month 4 to mid month 5: Incidence rates and point/period prevalence, with explicit denominator populations, observation rules and CIs.
F06.7 Study Templates & Qualification Records, early to mid month 5: Pre-configured packages with inputs, assumptions and diagnostics, each qualified against independent reference results.
The packages analyse datasets; they do not derive variables (F05) or format final outputs (F07). Selected open-source packages, such as TreatmentPatterns and DrugUtilisation, are integrated through defined input adapters, with pinned versions qualified for their intended use against independent references. Treatment sequences are derived once, in the engine (F05), and analysed here; an adapter test confirms this layer does not reconstruct a different treatment history. Dataset structures and module interfaces are defined in F05. Modules that estimate quantities from defined study inputs belong here; modules that derive study variables run in F05, so the same logic is not implemented twice. Packages are classed as required for the initial use cases, included if source prerequisites are met, or later extensions. Propensity-score matching and weighting are out of scope for the first release. The plots here are for exploring results; publication-ready figures are packaged in F07.
AI assistance here: drafts the analysis configuration for review; suggests the plot type for each result; drafts pathway configuration for review; drafts model configuration; reviewed modules estimate; recommends a template from the protocol. AI interprets, proposes and investigates; deterministic software executes and checks; authorized people approve scientific intent, material configuration changes and releases.
Acceptance gates: Core analyses available (end of month 4); Outcomes ready for qualification (mid month 5); Packages qualified (end of month 5).
Depends on: Analysis datasets (F05); Existing R module library; Supported R runtime on Databricks (confirmation due Month 1).

## Slide 5
RWDPLATFORM / GOVERNED ANALYTICS DELIVERY
F07 | Evidence Outputs: TFLs & Insight Views
F07 · Months 4–5
Study reporting and insight views on one governed layer: versioned results, TFL packages, and feasibility and data-quality views.
OUTCOME
Every study gets a traceable reporting package, and feasibility and data-quality views show their denominators and data-cut versions.
DEPENDS ON
Versioned analysis results (F06) · Analysis datasets (F05) · Qualified sources (F04) · Hosting environment · Data licence terms
DELIVERABLE
AI ASSISTANCE
RESULTS + VIEWS
REPORTING, REVIEW + RELEASE
Month 4
Month 5
EVIDENCE OUTPUTS
F07.1
Versioned Results Store
Versioned analysis results supply study TFLs; versioned source and cohort metrics supply feasibility and quality views
F07.2
Population Explorer & Attrition Funnel
Source suitability and study feasibility: populations, coverage and attrition under agreed candidate rules, with denominators
Summarizes suitability and feasibility findings
F07.3
One-Click Report Generation
Generates the agreed TFL package from a selected results version, using approved templates and GSK conventions
Drafts study-specific shells for review
F07.4
Completeness Dashboard
Completeness, plausibility and conformance of derived variables, by source and data cut
Flags data-quality anomalies for review
F07.5
Results Review & Reconciliation Workspace
Deterministic checks of values, denominators, labels, rounding and versions; reviewers approve or return each output
Flags suspicious patterns for review
F07.6
Narrative, Summary Slides & Release
Statistician-reviewed narrative and summary slides; versioned release, with re-approval if inputs change
Drafts narratives and summary slides for review
ACCEPTANCE GATES | WORKSTREAMS RUN IN PARALLEL; GATES CONTROL USE OF APPROVED INPUTS AND PROMOTION OF RELEASES
LATE MONTH 4 · RESULTS & EXPLORER ON TEST INPUTS
Versioned results and feasibility views testable
MID MONTH 5 · REPORTING READY FOR QUALIFICATION
TFL packages and completeness views integrated
END OF MONTH 5 · PILOT OUTPUTS ACCEPTED
Reconciled, reviewed and signed off
Notes: F07 Evidence Outputs: TFLs & Insight Views runs across months 4 to 5. Every study gets a traceable reporting package, and feasibility and data-quality views show their denominators and data-cut versions.
F07.1 Versioned Results Store, early to mid month 4: Versioned analysis results supply study TFLs; versioned source and cohort metrics supply feasibility and quality views.
F07.2 Population Explorer & Attrition Funnel, mid month 4 to early month 5: Source suitability and study feasibility: populations, coverage and attrition under agreed candidate rules, with denominators.
F07.3 One-Click Report Generation, mid month 4 to mid month 5: Generates the agreed TFL package from a selected results version, using approved templates and GSK conventions.
F07.4 Completeness Dashboard, late month 4 to mid month 5: Completeness, plausibility and conformance of derived variables, by source and data cut.
F07.5 Results Review & Reconciliation Workspace, late month 4 to mid month 5: Deterministic checks of values, denominators, labels, rounding and versions; reviewers approve or return each output.
F07.6 Narrative, Summary Slides & Release, mid to late month 5: Statistician-reviewed narrative and summary slides; versioned release, with re-approval if inputs change.
Evidence outputs present results and governed views; they do not run analyses (F06) or derive data (F05). Reporting draws on versioned analysis results, while feasibility and quality views draw on the qualified source, candidate cohorts or study dataset as appropriate, and access controls apply before any live-data view is shown. Numerical reconciliation is a deterministic software check, not an AI task, and covers titles, numbering, units, rounding and footnotes as well as values. Changing a dataset, analysis configuration or result version invalidates the affected output approvals. Output formats are confirmed for the initial use cases rather than assumed. Safety outputs are a later extension unless an agreed safety module is added to F06.
AI assistance here: summarizes suitability and feasibility findings; drafts study-specific shells for review; flags data-quality anomalies for review; flags suspicious patterns for review; drafts narratives and summary slides for review. AI interprets, proposes and investigates; deterministic software executes and checks; authorized people approve scientific intent, material configuration changes and releases.
Acceptance gates: Results & explorer on test inputs (late month 4); Reporting ready for qualification (mid month 5); Pilot outputs accepted (end of month 5).
Depends on: Versioned analysis results (F06); Analysis datasets (F05); Qualified sources (F04); Hosting environment; Data licence terms.